## Sheet1
www.rainbird.com Drupal Go Live Plan
Thursday May 10, 10:00 pm PDT
800-700-7989 code 483002
Step | Action | Who
GO LIVE
1 | Open firewall on PROD (52.8.167.217) to general traffic access for ports 80 and 443 | Rain Bird / Charley
2 | Create new subdomain DNS entry for OLD (52.8.37.17) as ww3.rainbird.com so that www.rainbird.com/au and www.rainbird.com/ca can remain active with files from the current site | Rain Bird / Charley
3 | Set up redirect from Drupal for Rain Bird Australia: www.rainbird.com/au --> ww3.rainbird.com/au | 5 Nerds
4 | Set up redirect from Drupal for Rain Bird Canada www.rainbird.com/ca --> ww3.rainbird.com/ca | 5 Nerds
5 | Change DNS for www.rainbird.com from OLD to PROD | Rain Bird / Charley
6 | Flush Drupal cache | 5 Nerds
7 | Clear SOLR index and run sitewide reindex | 5 Nerds
8 | Finish configuring SSL on PROD with signed certificate | 5 Nerds
TEST
9 | View home page from desktop browser outside of Rain Bird network (not on VPN) | Rain Bird / Alex
10 | View all persona home pages | Rain Bird / Alex
11 | View product category and detail pages, test document language filtering, video selection/playing, image gallery display and navigation | Rain Bird / Alex
12 | View support index, support detail pages in Homeowner, Professional, Ag
13 | View document library in Professional, Golf and Ag. Test filters, search. | Rain Bird / Alex
14 | Test contractor referral lookup and results in Homeowner section | Rain Bird / Alex
15 | Test job listings search in Careers section | Rain Bird / Alex
16 | Test site search including persona filters | Rain Bird / Alex
17 | Submit a test form, confirm correct processing | Rain Bird / Alex
18 | View and navigate press releases | Rain Bird / Alex
19 | Test mobile on tablet and phone, confirm responsive layouts and navigation working | Rain Bird / Alex
20 | Login to Rain Bird VPN and log in to PROD admin area | Rain Bird / Alex
21 | Test Admin existing product and basic page edit functionality | Rain Bird / Alex
22 | Test Admin upload new document and new image | Rain Bird / Alex
23 | Test Admin create new basic page and new product page | Rain Bird / Alex
24 | Test Admin content version rollback | Rain Bird / Alex
CONTINGENCY
25 | If major issues are encountered that cannot be quickly corrected, change DNS entry for www.rainbird.com back to OLD ip | Rain Bird / Charley
INFORM/MONITOR
26 | Send distribution P announcement to inform Rain Bird personnel of new site live status, encourage site visits and sending of feedback, desired improvements vs bugs/errors | Rain Bird / Alex
27 | Monitor traffic and resources, site performance to confirm stability | All
SEO
28 | Place Google Webmaster Confirmation file (googleb3b059d6b8159a0b.html) at web root to allow Google Webmaster Tools to confirm site ownership. | 5 Nerds
29 | Configure 301 redirects based on Excel file provided by Alex | 5 Nerds
30 | Generate new XML sitemap via link crawl. | Rain Bird / Alex
31 | Place new sitemap.xml file at web root so it can be accessed by Google for site indexing. | Rain Bird / Alex
32 | Submit updated sitemap via Google Webmaster Tools for reindexing | Rain Bird / Alex